## Original
Task | FED Low | FED High | BED Low | BED High | Arch Low | Arch High | QA/BA Low | QA/BA High | BA Low | BA High | PM Low | PM High | Gov Low | Gov High | Comments
Onboarding
Project setup | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 |  |  | 4 | 6 | 0 | 0
Discovery workshops | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 |  |  | 2 | 2 | 0 | 0
Local Dev Setup | 4 | 4 | 4 | 4 | 1 | 1 |  |  |  |  | 1.35 | 1.35 | 0 | 0
Functional Spec | 0 | 0 | 0 | 0 | 2 | 3 | 16 | 20 |  |  | 2.7 | 3.45 | 0 | 0
ADO test case setup | 0 | 0 | 0 | 0 | 2 | 3 | 16 | 20 |  |  | 2.7 | 3.45 | 0 | 0
Implementation | [10 empty] | 0 | 0 | 0 | 0
0
Content and Layout | [12 empty] | 0
Content Migration (11,700+ pages) |  |  |  |  | 8 | 12 | [6 empty] | 0
Media Migration |  |  |  |  | 3 | 6 | [6 empty] | 0
Multilingual & Language fallback configuration |  |  | 6 | 8 | 0.75 | 1 | [6 empty] | 0
Component migration |  |  |  |  | 2 | 4 | [6 empty] | 0
Component conversion (112 in total: 50 simple, 30 medium, 20 hard, 12 search) |  |  | 200 | 450 | [8 empty] | 0
Create XM Cloud Pages Branches (for self-service pages, unknown count) |  |  | 6 | 12 | [8 empty] | 0
Convert blog pages into generic XM Cloud pages with taxonomy support (~250 pages) |  |  | 8 | 12 | 4 | 16 | [6 empty] | 0
Forms | [12 empty] | 0 | 0
Forms analysis |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Recreate forms in Sitecore Forms (assume ~10) |  |  | 12 | 20 | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 4.125 | 0.48125
Field validations, actions, integrations |  |  | 16 | 20 | 2 | 2.5 | 4 | 5 |  |  | 3.3 | 4.125 | 0.48125
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Search Migration (Solr to Sitecore Search) | [12 empty] | 0
Existing search analysis: understand facets, indexes, PDFs |  |  |  |  | 6 | 10 | 0 | 0 |  |  | 0.9 | 1.5 | 0
Schema mapping: data fields, tokenization, analyzers |  |  | 6 | 10 | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 2.0625 | 0
Sitecore Search setup: crawl, index, synonyms, stop words |  |  | 20 | 32 | 2.5 | 4 | 5 | 8 |  |  | 4.125 | 6.6 | 0
PDF indexing setup: Enable parsing and search for PDFs |  |  | 6 | 10 | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 2.0625 | 0
Faceted UI refactoring: changes for new API |  |  | 12 | 20 | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 4.125 | 0
React component adjustments (to match styling and UX) |  |  | 12 | 20 | 0 | 2.5 | 0 | 5 |  |  | 0 | 4.125 | 0
Security-related | [12 empty] | 0
User & Role Audit |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Azure B2C: configure Microsoft Entra ID B2C for XM Cloud, setup user flows |  |  | 8 | 16 | 1 | 2 | 2 | 4 |  |  | 1.65 | 3.3 | 0
Migrate Users & Roles to B2C: create/import users and roles, test mappings, test field claims |  |  | 10 | 16 | 1.25 | 2 | 2.5 | 4 |  |  | 2.0625 | 3.3 | 0
Send email invitations or password reset links |  |  | 2 | 6 | 0.25 | 0.75 | 0.5 | 1.5 |  |  | 0.4125 | 1.2375 | 0 | 0
SSO Enablement: Configure OIDC for SSO between XM Cloud & Azure B2C |  |  | 6 | 10 | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 2.0625 | 0
Identify and update workflows to match XM Cloud schema |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Secure connection XM Cloud to Azure-hosted SMTP (Entra App reg., client secret, scopes) |  |  | 8 | 12 | 1 | 1.5 | 2 | 3 |  |  | 1.65 | 2.475 | 0
Azure DevOps CI/CD Setup with extra security scan (GitHub + Azure for XM Cloud deploys) |  |  | 8 | 12 | 1 | 1.5 | 2 | 3 |  |  | 1.65 | 2.475 | 0
Miscellaneous | [12 empty] | 0
Next.js app integrations (Google Analytics, GTM, OneTrust, GetResponse, Zoho, Agiloft) |  |  | 16 | 32 | 2 | 4 | 4 | 8 |  |  | 3.3 | 6.6 | 0
Adjusting styles misalignmanets and adressing scripts issues | 12 | 24 | 2 | 4 | 1.75 | 3.5 | 3.5 | 7 |  |  | 2.8875 | 3.975 | 0
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Compliance and Accessibility |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Carry over ADA 508: validate and adjust markup for compliance |  |  | 8 | 10 | 1 | 1.25 | 2 | 2.5 |  |  | 1.65 | 2.0625 | 0 | 0
Privacy (cookie, consent, etc.): check changes needed for the new hosting (if any) |  |  | 2 | 6 | 0.25 | 0.75 | 0.5 | 1.5 |  |  | 0.4125 | 1.2375 | 0 | 0
0
[13 empty] | 0 | 0
Code reviews | 3 | 4 | 8 | 10 | 1.375 | 1.75 |  |  |  |  | 1.8562 | 2.2125 | 0 | 0
Bug fixes (15% - critical) | 5 | 6 | 10 | 12 | 1.875 | 2.25 | 3.75 | 4.5 |  |  | 3.0938 | 3.5625 | 0 | 0
Additional fixes for all but low bugs | 4 | 4 | 6 | 8 | 1.25 | 1.5 | 2.5 | 3 |  |  | 2.0625 | 2.475 | 0 | 0
Page speed test | 4 | 6 | 1 | 1 | 0.625 | 0.875 | 1.25 | 1.75 |  |  | 1.0312 | 1.1438 | 0 | 0
Pen test issue mitigation | 3 | 4 | 6 | 8 | 1.125 | 1.5 | 2.25 | 3 |  |  | 1.8562 | 2.325 | 0 | 0
Regression test | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 |  |  | 1.2 | 2.4 | 0 | 0
Accessibility issue fixes | 3 | 4 | 4 | 6 | 0.875 | 1.25 | 1.75 | 2.5 |  |  | 1.4437 | 1.9125 | 0 | 0
UAT | 6 | 8 | 8 | 12 | 1.75 | 2.5 | 3.5 | 5 |  |  | 2.8875 | 3.825 | 0 | 0 | 1 week of uat
Documentation | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Technical Design Document | 0 | 1 | 0 | 1 | 2 | 3 | 0 |  |  |  | 0.3 | 0.6 | 0 | 0
Training and handoff sessions | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Content author training session |  |  |  |  | 2 | 2 | 0 | 0 |  |  | 0.3 | 0.3 | 0 | 0 | prep and 1hr session
Technical handoff of assets |  |  |  |  | 1 | 1 | 0 | 0 |  |  | 0.15 | 0.15 | 0 | 0 | prep and 1hr session
Content authoring videos and manual creation | [6 empty] | 6 | 8 |  |  | 0.9 | 1.2 | 0 | 0 | authoring manual generated with AI from videos.
Deployments |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
DEV |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
QA |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
PROD |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0 | 0 | 1 deployment support
Subtotal | 44 | 65 | 433 | 820 | 65.375 | 114.125 | 108.5 | 166.75 | 0 | 0 | 64.9687 | 99.9312 | 0.9625 | 0
Agile | 6.6 | 9.75 | 64.95 | 123 | 9.8063 | 17.1187 | 16.275 | 25.0125 | 0 | 0 | 9.7453 | 14.9897 | 0.14438 | 0
Total Hours | 50.6 | 74.75 | 497.95 | 943 | 75.1813 | 131.2438 | 124.775 | 191.7625 | 0 | 0 | 74.7141 | 114.9209 | 1.1069 | 0
Total w/Buffer | 55.66 | 82.225 | 547.745 | 1037.3 | 82.6994 | 144.3681 | 137.2525 | 210.9387 | 0 | 0 | 82.1855 | 126.413 | 1.2176 | 0
Weeks | 1.3915 | 2.0556 | 13.6936 | 25.9325 | 2.0675 | 3.6092 | 3.4313 | 5.2735 | 0 | 0 | 2.0546 | 3.1603 | 0.030439 | 0
Rate | 100 | 100 | 100 | 100 | 150 | 150 | 95 | 95 | 90 | 90 | 125 | 125 | 240 | 240
Cost | 5566 | 8222.5 | 54774.5 | 103730 | 12404.9063 | 21655.2188 | 13038.9875 | 20039.1813 | 0 | 0 | 10273.1836 | 15801.6289 | 292.215 | 0
Assumptions |  |  |  |  | Low | Mid | High
Changes apply to IB.com only |  |  |  |  | 96349.7923 | 132899.1606 | 169448.5289
same product workflow reused for new products
no roles or access config
Figma provided by client
Grid used in Figma |  |  | Agile | QA
|  |  | 15% | 25%
|  |  | PM | Buffer
|  |  | 15% | 10%
Gov
0%

## Reduced (hidden)
Task | FED Low | FED High | BED Low | BED High | Arch Low | Arch High | QA/BA Low | QA/BA High | BA Low | BA High | PM Low | PM High | Gov Low | Gov High | Comments
Onboarding
Project setup | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 |  |  | 4 | 6 | 0 | 0
Discovery workshops | 0 | 0 | 0 | 0 | 1 | 2 | 8 | 12 |  |  | 2 | 2 | 0 | 0
Local Dev Setup | 2 | 6 | 8 | 12 | 1 | 1 |  |  |  |  | 1.65 | 2.25 | 0 | 0
Functional Spec | 0 | 0 | 0 | 0 | 2 | 3 | 32 | 40 |  |  | 5.1 | 6.45 | 0 | 0
ADO test case setup
Implementation | [10 empty] | 0 | 0 | 0 | 0
0
Content and Layout | [12 empty] | 0
Content Migration (11,700+ pages) |  |  |  |  | 8 | 12 | [6 empty] | 0
Media Migration |  |  |  |  | 3 | 6 | [6 empty] | 0
Multilingual & Language fallback configuration |  |  | 6 | 8 | 0.75 | 1 | [6 empty] | 0
Component migration |  |  |  |  | 2 | 4 | [6 empty] | 0
Component conversion (112 in total: 50 simple, 30 medium, 20 hard, 12 search) | 200 | 450 | [10 empty] | 0
Create XM Cloud Pages Branches (for self-service pages, unknown count) |  |  | 6 | 12 | [8 empty] | 0
Convert blog pages into generic XM Cloud pages with taxonomy support (~250 pages) |  |  | 8 | 12 | 4 | 16 | [6 empty] | 0
Forms | [12 empty] | 0 | 0
Forms analysis |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Recreate forms in Sitecore Forms (assume ~10) |  |  | 12 | 20 | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 4.125 | 0.48125
Field validations, actions, integrations |  |  | 16 | 20 | 2 | 2.5 | 4 | 5 |  |  | 3.3 | 4.125 | 0.48125
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Search Migration (Solr to Sitecore Search) | [12 empty] | 0
0
Existing search analysis: understand facets, indexes, PDFs |  |  |  |  | 6 | 10 | 0 | 0 |  |  | 0.9 | 1.5 | 0
Schema mapping: data fields, tokenization, analyzers |  |  | 6 | 10 | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 2.0625 | 0
Sitecore Search setup: crawl, index, synonyms, stop words |  |  | 10 | 16 | 1.25 | 2 | 2.5 | 4 |  |  | 2.0625 | 3.3 | 0
PDF indexing setup: Enable parsing and search for PDFs |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Faceted UI refactoring: changes for new API | 12 | 20 |  |  | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 2.925 | 0
React component adjustments (to match styling and UX) | 12 | 20 |  |  | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 2.925 | 0
Security-related |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
User & Role Audit |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Azure B2C: configure Microsoft Entra ID B2C for XM Cloud, setup user flows
Migrate Users & Roles to B2C: create/import users and roles, test mappings, test field claims
Send email invitations or password reset links |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
SSO Enablement: Configure OIDC for SSO between XM Cloud & Azure B2C | 6 | 10 |  |  | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 1.4625 | 0
Identify and update workflows to match XM Cloud schema |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Secure connection XM Cloud to Azure-hosted SMTP (Entra App reg., client secret, scopes) |  |  | 10 | 16 | 1.25 | 2 | 2.5 | 4 |  |  | 2.0625 | 3.3 | 0
Azure DevOps CI/CD Setup with extra security scan (GitHub + Azure for XM Cloud deploys) |  |  | 1 | 2 | 0.125 | 0.25 | 0.25 | 0.5 |  |  | 0.20625 | 0.4125 | 0
Miscellaneous | [12 empty] | 0
Next.js app integrations (GTM, GetResponse, Zoho, Agiloft) | 40 | 56 |  |  | 5 | 7 | 10 | 14 |  |  | 8.25 | 9.15 | 0
Adjusting styles misalignmanets and adressing scripts issues | 12 | 24 | 2 | 4 | 1.75 | 3.5 | 3.5 | 7 |  |  | 2.8875 | 3.975 | 0
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Compliance and Accessibility |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Carry over ADA 508: validate and adjust markup for compliance | 8 | 10 |  |  | 1 | 1.25 | 2 | 2.5 |  |  | 1.65 | 1.7625 | 0 | 0
Privacy (cookie, consent, etc.): check changes needed for the new hosting (if any)
Visual regression test | [6 empty] | 8 | 16 |  |  |  |  | 0
Content deployment from local to cloud |  |  |  |  | 8 | 16 | 0 | 0 |  |  | 1.2 | 2.4 | 0 | 0
Code reviews | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Bug fixes (15% - critical) |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Additional fixes for all but low bugs
Page speed test
Pen test issue mitigation
Regression test | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 |  |  | 1.2 | 2.4 | 0 | 0
Accessibility issue fixes
UAT | 40 | 60 |  |  | 5 | 7.5 | 10 | 15 |  |  | 8.25 | 9.375 | 0 | 0 | 2 weeks
Documentation | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Technical Design Document | 0 | 1 | 0 | 1 | 8 | 12 | 0 |  |  |  | 1.2 | 1.95 | 0 | 0
Training and handoff sessions | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Content author training session |  |  |  |  | 2 | 2 | 0 | 0 |  |  | 0.3 | 0.3 | 0 | 0 | prep and 1hr session
Technical handoff of assets |  |  |  |  | 1 | 1 | 0 | 0 |  |  | 0.15 | 0.15 | 0 | 0 | prep and 1hr session
Content authoring videos and manual creation | [10 empty] | 0 | 0 | 0 | 0 | authoring manual generated with AI from videos.
Deployments |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
DEV |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
QA |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
PROD |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0 | 0 | 1 deployment support
Subtotal | 332 | 657 | 97 | 153 | 72.625 | 125.5 | 109.75 | 165 | 0 | 0 | 58.7438 | 78.425 | 0.9625 | 0
Agile | 49.8 | 98.55 | 14.55 | 22.95 | 10.8937 | 18.825 | 16.4625 | 24.75 | 0 | 0 | 8.8116 | 11.7638 | 0.14438 | 0
Total Hours | 381.8 | 755.55 | 111.55 | 175.95 | 83.5187 | 144.325 | 126.2125 | 189.75 | 0 | 0 | 67.5553 | 90.1888 | 1.1069 | 0
Total w/Buffer | 419.98 | 831.105 | 122.705 | 193.545 | 91.8706 | 158.7575 | 138.8338 | 208.725 | 0 | 0 | 74.3108 | 99.2076 | 1.2176 | 0
Weeks | 10.4995 | 20.7776 | 3.0676 | 4.8386 | 2.2968 | 3.9689 | 3.4708 | 5.2181 | 0 | 0 | 1.8578 | 2.4802 | 0.030439 | 0
Rate | 90 | 90 | 90 | 90 | 130 | 130 | 95 | 95 | 85 | 85 | 110 | 110 | 240 | 240
Cost | 37798.2 | 74799.45 | 11043.45 | 17419.05 | 11943.1812 | 20638.475 | 13189.2063 | 19828.875 | 0 | 0 | 8174.1928 | 10912.8388 | 292.215 | 0
Assumptions |  |  |  |  | Low | Mid | High
[5 empty] | 82440.4453 | 113019.567 | 143598.6888
|  |  |  | Goal | 75k
|  |  | Agile | QA
|  |  | 15% | 25%
|  |  | PM | Buffer
|  |  | 15% | 15%
Gov
0%

## LT Rates Reduced
Task | FED Low | FED High | BED Low | BED High | Arch Low | Arch High | QA/BA Low | QA/BA High | BA Low | BA High | PM Low | PM High | Gov Low | Gov High | Comments
Onboarding
Project setup | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 |  |  | 4 | 6 | 0 | 0
Discovery workshops | 0 | 0 | 0 | 0 | 1 | 2 | 8 | 12 |  |  | 2 | 2 | 0 | 0
Local Dev Setup | 2 | 6 | 8 | 12 | 1 | 1 |  |  |  |  | 1.65 | 2.25 | 0 | 0
Functional Spec | 0 | 0 | 0 | 0 | 2 | 3 | 32 | 40 |  |  | 5.1 | 6.45 | 0 | 0
ADO test case setup
Implementation | [10 empty] | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
Content and Layout | [10 empty] | 0 | 0 | 0
Content Migration (11,700+ pages) |  |  |  |  | 8 | 12 |  |  |  |  | 1.2 | 1.8 | 0
Media Migration |  |  |  |  | 3 | 6 |  |  |  |  | 0.45 | 0.9 | 0
Multilingual & Language fallback configuration |  |  | 6 | 8 | 0.75 | 1 |  |  |  |  | 1.0125 | 1.35 | 0
Component migration |  |  |  |  | 2 | 4 | 0 | 0 |  |  | 0.3 | 0.6 | 0
Component conversion (112 in total: 50 simple, 30 medium, 20 hard, 12 search) | 200 | 350 |  |  | 2 | 4 | 50 | 87.5 |  |  | 37.8 | 43.725 | 0
Create XM Cloud Pages Branches (for self-service pages, unknown count) |  |  | 6 | 12 | [6 empty] | 0.9 | 1.8 | 0
Convert blog pages into generic XM Cloud pages with taxonomy support (~250 pages) |  |  | 8 | 12 | 4 | 16 |  |  |  |  | 1.8 | 4.2 | 0
Forms | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Forms analysis |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Recreate forms in Sitecore Forms (assume ~10) |  |  | 12 | 20 | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 4.125
Field validations, actions, integrations |  |  | 16 | 20 | 2 | 2.5 | 4 | 5 |  |  | 3.3 | 4.125
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Search Migration (Solr to Sitecore Search) | [12 empty] | 0
0
Existing search analysis: understand facets, indexes, PDFs |  |  |  |  | 6 | 10 | 0 | 0 |  |  | 0.9 | 1.5 | 0
Schema mapping: data fields, tokenization, analyzers |  |  | 6 | 10 | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 2.0625 | 0
Sitecore Search setup: crawl, index, synonyms, stop words |  |  | 10 | 16 | 1.25 | 2 | 2.5 | 4 |  |  | 2.0625 | 3.3 | 0
PDF indexing setup: Enable parsing and search for PDFs |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Faceted UI refactoring: changes for new API | 8 | 12 |  |  | 1 | 1.5 | 2 | 3 |  |  | 1.65 | 1.875 | 0
React component adjustments (to match styling and UX) | 12 | 20 |  |  | 1.5 | 2.5 | 3 | 5 |  |  | 2.475 | 2.925 | 0
Security-related |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
User & Role Audit |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0
Azure B2C: configure Microsoft Entra ID B2C for XM Cloud, setup user flows
Migrate Users & Roles to B2C: create/import users and roles, test mappings, test field claims
Send email invitations or password reset links |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
SSO Enablement: Configure OIDC for SSO between XM Cloud & Azure B2C | 6 | 10 |  |  | 0.75 | 1.25 | 1.5 | 2.5 |  |  | 1.2375 | 1.4625 | 0
Identify and update workflows to match XM Cloud schema |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Secure connection XM Cloud to Azure-hosted SMTP (Entra App reg., client secret, scopes) |  |  | 10 | 16 | 1.25 | 2 | 2.5 | 4 |  |  | 2.0625 | 3.3 | 0
Azure DevOps CI/CD Setup with extra security scan (GitHub + Azure for XM Cloud deploys) |  |  | 1 | 2 | 0.125 | 0.25 | 0.25 | 0.5 |  |  | 0.20625 | 0.4125 | 0
Miscellaneous | [12 empty] | 0
Next.js app integrations (GTM, GetResponse, Zoho, Agiloft) | 40 | 56 |  |  | 5 | 7 | 10 | 14 |  |  | 8.25 | 9.15 | 0
Adjusting styles misalignmanets and adressing scripts issues | 12 | 24 | 2 | 4 | 1.75 | 3.5 | 3.5 | 7 |  |  | 2.8875 | 3.975 | 0
Compliance and Accessibility |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Carry over ADA 508: validate and adjust markup for compliance |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Privacy (cookie, consent, etc.): check changes needed for the new hosting (if any)
Visual regression test | [6 empty] | 8 | 16 |  |  |  |  | 0
Content deployment from local to cloud |  |  |  |  | 8 | 16 | 0 | 0 |  |  | 1.2 | 2.4 | 0 | 0
Code reviews | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Bug fixes (15% - critical) |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Additional fixes for all but low bugs
Page speed test
Pen test issue mitigation
Regression test | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 |  |  | 1.2 | 2.4 | 0 | 0
Accessibility issue fixes
UAT | 40 | 60 |  |  | 5 | 7.5 | 10 | 15 |  |  | 8.25 | 9.375 | 0 | 0 | 2 weeks
Documentation | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Technical Design Document | 0 | 1 | 0 | 1 | 8 | 12 | 0 |  |  |  | 1.2 | 1.95 | 0 | 0
Training and handoff sessions | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Content author training session |  |  |  |  | 2 | 2 | 0 | 0 |  |  | 0.3 | 0.3 | 0 | 0 | prep and 1hr session
Technical handoff of assets |  |  |  |  | 1 | 1 | 0 | 0 |  |  | 0.15 | 0.15 | 0 | 0 | prep and 1hr session
Content authoring videos and manual creation | [10 empty] | 0 | 0 | 0 | 0 | authoring manual generated with AI from videos.
Deployments |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
DEV |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
QA |  |  | 3 | 4 | 0.375 | 0.5 | 0.75 | 1 |  |  | 0.61875 | 0.825 | 0 | 0 | 4 deployments
PROD |  |  | 2 | 4 | 0.25 | 0.5 | 0.5 | 1 |  |  | 0.4125 | 0.825 | 0 | 0 | 1 deployment support
Subtotal | 320 | 539 | 97 | 153 | 73.125 | 127.25 | 156.75 | 248 | 0 | 0 | 99.7313 | 129.9875 | 0 | 0
Agile | 48 | 80.85 | 14.55 | 22.95 | 10.9688 | 19.0875 | 23.5125 | 37.2 | 0 | 0 | 14.9597 | 19.4981 | 0 | 0
Total Hours | 368 | 619.85 | 111.55 | 175.95 | 84.0938 | 146.3375 | 180.2625 | 285.2 | 0 | 0 | 114.6909 | 149.4856 | 0 | 0
Total w/Buffer | 404.8 | 681.835 | 122.705 | 193.545 | 92.5031 | 160.9713 | 198.2887 | 313.72 | 0 | 0 | 126.16 | 164.4342 | 0 | 0
Weeks | 10.12 | 17.0459 | 3.0676 | 4.8386 | 2.3126 | 4.0243 | 4.9572 | 7.843 | 0 | 0 | 3.154 | 4.1109 | 0 | 0
Rate | 80 | 80 | 80 | 80 | 120 | 120 | 75 | 75 | 85 | 85 | 100 | 100 | 240 | 240
Cost | 32384 | 54546.8 | 9816.4 | 15483.6 | 11100.375 | 19316.55 | 14871.6562 | 23529 | 0 | 0 | 12616.0031 | 16443.4187 | 0 | 0
Assumptions |  |  |  |  | Low | Mid | High
[5 empty] | 80788.4344 | 105053.9016 | 129319.3688
|  |  |  | Goal | 75k | 95k
[6 empty] | w/o Rebate | Discount | Subtotal | Rebate | Total Cost
[6 empty] | 105053.9016 | 15000 | 90053.9016 | 25000 | 65053.9016
Event: Sym or Roadshow
Video feedback
Webinar

## MS
Task | FED Low | FED High | BED Low | BED High | Arch Low | Arch High | QA/BA Low | QA/BA High | BA Low | BA High | PM Low | PM High | Gov Low | Gov High | Comments
MS | 80 | 80 |  |  | 40 | 40 | 20 | 20 |  |  | 21 | 21 | 0 | 0
[7 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Subtotal | 80 | 80 | 0 | 0 | 40 | 40 | 20 | 20 | 0 | 0 | 21 | 21 | 0 | 0
Agile | 12 | 12 | 0 | 0 | 6 | 6 | 3 | 3 | 0 | 0 | 3.15 | 3.15 | 0 | 0
Total Hours | 92 | 92 | 0 | 0 | 46 | 46 | 23 | 23 | 0 | 0 | 24.15 | 24.15 | 0 | 0
Total w/Buffer | 101.2 | 101.2 | 0 | 0 | 50.6 | 50.6 | 25.3 | 25.3 | 0 | 0 | 26.565 | 26.565 | 0 | 0
Weeks | 2.53 | 2.53 | 0 | 0 | 1.265 | 1.265 | 0.6325 | 0.6325 | 0 | 0 | 0.66413 | 0.66413 | 0 | 0
Rate | 80 | 80 | 80 | 80 | 120 | 120 | 75 | 75 | 85 | 85 | 100 | 100 | 240 | 240
Cost | 8096 | 8096 | 0 | 0 | 6072 | 6072 | 1897.5 | 1897.5 | 0 | 0 | 2656.5 | 2656.5 | 0 | 0
Assumptions |  |  |  |  | Low | Mid | High
[5 empty] | 18722 | 18722 | 18722
|  |  |  | Goal | 75k | 96k
[5 empty] | Mid | w/o Rebate | Discount | Final
[5 empty] | 17785.9 | -7214.1 | 18000 | -25214.1

## Assumptions and notes
We consider Lift & Shift approach to reach XM Cloud as soon as possible
We do not consider media migration to the Content Hub - it will retain existing configuration (Media Library + external blob storage)
We do not migrate existing xDB since that does not bring any value
We do not consider personalization at this scope of work
GA, default,
OneTrust - existing code drop
Functional regression testing by the client

## Sheet2 (hidden)
Task | FED Low | FED High | BED Low | BED High | Arch Low | Arch High | QA Low | QA High | BA Low | BA High | PM Low | PM High | Comments
| 47 | 76 | 40 | 66 | 12 | 15.5 | 19 | 26 | 0 | 0
Onboarding | 8 | 8 | 8 | 8 | 2 | 4 | 8 | 8
Local Dev Setup | 8 | 16 | 8 | 16 | 3 | 4 | 4 | 8
License Plate tab FE | 12 | 16 |  |  | 1.5 | 2 | 3 | 4
VIN search tab FE | 12 | 16 |  |  | 1.5 | 2 | 3 | 4
Backend implementation for License plate to vehicle model conversion |  |  | 4 | 8 | 1 | 1 | 1 | 2
Backend implementation for VIN to vehicle model conversion |  |  | 12 | 20 | 3 | 2.5
Documentation Updates |  |  | 2 | 3 | 2 | 4
Technical handoff |  |  |  |  | 1 | 1
Page speed load test | 1 | 1 |  |  | 0.5 | 1
Bugfixing | 4 | 16 | 4 | 8 | 1.5 | 3
UAT | 2 | 3 | 2 | 3 | 0.75 | 0.75
Deployments |  |  |  |  | 0 | 0
DEV
QA
PROD
Subtotal | 47 | 76 | 40 | 66 | 17.75 | 25.25 | 19 | 26 | 0 | 0 | 0 | 0
Agile | 7.05 | 11.4 | 6 | 9.9 | 2.6625 | 3.7875 | 2.85 | 3.9 | 0 | 0 | 0 | 0
Total Hours | 54.05 | 87.4 | 46 | 75.9 | 20.4125 | 29.0375 | 21.85 | 29.9 | 0 | 0 | 0 | 0
Rate | 85 | 85 | 85 | 85 | 95 | 95 | 55 | 55 | 55 | 55 | 95 | 95
Cost | 4594.25 | 7429 | 3910 | 6451.5 | 1939.1875 | 2758.5625 | 1201.75 | 1644.5 | 0 | 0 | 0 | 0
Assumptions |  |  |  |  | Low | Mid | High
Integration for License->Car model available |  |  |  |  | 11645.1875 | 14964.375 | 18283.5625
Integration for VIN->Car model available (is it?)
No new component development, change to existing Stacked finder rendering
Page load speed test included
Performance depends on integrations, no additional cache logic in scope |  |  | Agile | QA
Components developed with accessibility requirements |  |  | 15% | 25%
No test automation |  |  | PM
Most likely FED and BED are same person (then cut onboarding time) |  |  | 15%